## Slide 1
FY14 Efficiencies Goal:
FY14 Flash:
Stellar BI – Indirect Business
On Track | Low Risk | Critical | Complete | Not Started
Business Lead | Cameron Vine
HP Team | 
ShineTech Team | Robin
Omni360 Team | Pablo
Updated: Jun 16th , 2021
Purpose: Improve reports with more accurate information.
Objectives: Daily basis feeds thru streaming solution for Stellar Indirect Business BI tools
Key Milestones | Status | Start Date | End Date
DoD Closing and Sign Off | 100% |  | 
Kick-Off | 100% |  | 
Magento Infrastructure - Stellar team | 100% |  | 
Database preparation - Stellar team & Replicas | 100% |  | 
Data Encrtp/Decrp - Stellar team | 100% |  | 
India-Reverse Eng Tables Build | 70% | Jun 8 | Jun 22
India-Design Report View | 50% | Jun 8 | Jun 25
India- Load initial Historical Data | 0% | Jun 28 | Jul 9
Transformation – Tokenization process | 0% | Jul 12 | Jul 30
India-PII data Identification and Tokenization | 0% | Jul 19 | Jul 30
India-Lambda Update Reports | 0% | Jul 19 | Jul 30
India-Historical validation | 0% | Jul 30 | Aug 5
India-Load Tokenize Historical data | 0% | Aug 5 | Aug 13
India-Validate Data flow | 0% | Aug 20 | Aug 25
India-Report feed to Stellar BI | 0% | Aug 30 | Sep 3 go live
India-Report Monitoring | 0% | Aug 20 | Sep 3
  Accomplishments
18 New schema tables in O360 RDS
Data flowing for the 13 tables
3 views(“Reports”) structure completed
Increase scope to 23 tables
Review calculated fields and missing fields with Robin
Number of reports increased from 6 to 7
Next Steps
Overall Status | 
Development | 
Testing | 
Overall Status: Development (Streaming) WIP
Issues/Risks |  |  |  |  |  | 
Status | Types | Severity | Description | Mitigation/Next Steps | Owner | Due
 |  |  | 3 Reports at risk due to missing information on documentation |  | Robin |